## Forgot Password
S.No | Tasks | Duration (In hours) | Notes
1 | Header : Focus & Read logo. Footer : Focus & Read Footer Heading, language links.( Non English characters are not read by the screen reader). Reading Non English characters in Links, Contrast Ratio. | 2 | Need confirmation for design change to increase the contrast ratio. This is one time effort shall fix issues in all the pages and steps.
2 | Focus & Read Input text boxes, Forgot Username link, show character, I remember Password link, continue button, next button, submit button, back button, proceed to sign in button, Captcha reload button, Show characters links/buttons/icons for the Password fields. Focus and Read Password Text, Page heading and step heading. Adding alternative text to images such otp email image. Adding ARIA attributes for OTP related texts content "An email with a verification code was just sent to . ", "Didn't receive the code?", link "Request a new code" | 4 | ARIA attributes shall be added whereever needed.
3 | Focus & Read Success Page, Account Locked out page, Otp Account Locked out page, Otp Session expired page. Mobile Site Down Apologies page. Focus and Read the contents of the Password Help / Requirement Pop up. Password Srength indicator focus and reading. | 2 | ARIA attributes shall be added whereever needed.
4 | Focus & Read form validation Error Messages. | 2 | ARIA attributes shall be added whereever needed.
5 | WAM Error Messages. | 4 | ARIA attributes shall be added whereever needed.

## Registration
S.No | Tasks | Duration (In hours) | Notes
1 | Header : Focus & Read logo. Footer : Focus & Read Footer Heading, language links.( Non English characters are not read by the screen reader). Reading Non English characters in Links, Contrast Ratio. | 0 | Need confirmation for design change to increase the contrast ratio. This is one time effort shall fix issues in all the pages and steps.
2 | Focus & Read Input text boxes, continue button, next button, submit button, back button, proceed to sign in button, Captcha reload button,Show characters icon/link for the Password fields, Focus and Read Password Text, date Combo box, secutiry question dropdown boxes, text input fields, check box,SN or MemberID toggling. Page heading and step heading. Adding alternative text to images | 4 | ARIA attributes shall be added whereever needed.
3 | Success Page, Account Locked out page, already registered, mobile site down page | 2 | ARIA attributes shall be added whereever needed.
4 | Focus & Read form validation Error Messages. | 2 | ARIA attributes shall be added whereever needed.
5 | WAM Error Messages. | 4 | ARIA attributes shall be added whereever needed.

## Forgot Username
S.No | Tasks | Duration (In hours) | Notes
1 | Header : Focus & Read logo. Footer : Focus & Read Footer Heading, language links.( Non English characters are not read by the screen reader). Reading Non English characters in Links, Contrast Ratio. | 0 | Need confirmation for design change to increase the contrast ratio. This is one time effort shall fix issues in all the pages and steps.
2 | Focus & Read Input text boxes, continue button, submit button, back button, proceed to sign in button. Focus Captcha reload button, date Combo box, SN or MemberID toggling. Page heading and step heading. Adding alternative text to images | 4 | ARIA attributes shall be added whereever needed.
3 | Focus & Read Success Page, Account Locked out page, Mobile Site Down Apologies page. | 1 | ARIA attributes shall be added whereever needed.
4 | Focus & Read form validation Error Messages. | 1 | ARIA attributes shall be added whereever needed.
5 | WAM Error Messages. | 4 | ARIA attributes shall be added whereever needed.

## Reset Password
S.No | Tasks | Duration (In hours) | Notes
1 | Header : Focus & Read logo. Footer : Focus & Read Footer Heading, language links.( Non English characters are not read by the screen reader). Reading Non English characters in Links, Contrast Ratio. | 0 | Need confirmation for design change to increase the contrast ratio. This is one time effort shall fix issues in all the pages and steps.
2 | Focus & Read Input text boxes, Captcha reload button, Show characters for the Password fields, Password Text, security question dropdown boxes. | 1 | ARIA attributes shall be added whereever needed.
3 | Focus & Read Success Page, Account Locked out page, Mobile Site Down Apologies page. Focus and Read the contents of the Password Help / Requirement Pop up. | 1 | ARIA attributes shall be added whereever needed.
4 | Focus & Read form validation Error Messages. | 2 | ARIA attributes shall be added whereever needed.
5 | WAM Error Messages. | 4 | ARIA attributes shall be added whereever needed.